## Plan by Scenario
United Machining APQP Plan
| Part Number |  |  |  |  | Part Revision Level |  | Part Name |  | UM Purchase Order
| Drawing Number |  |  |  |  | Drawing Revision Level |  | UM Plant |  | SQAE ref
| Supplier Name |  |  |  |  | Supplier SAP Code |  | Document Date |  | Document version | rev.3 (ref. MS2)
Review | Item | APQP Scenario |  |  |  | Item description | Form | Responsibility | To be completed within | UM Focal Point(s) name | Notes
|  | A | B | C | D
PDR | Deliverable | ü | ü | û | û | Drawings & Key Characteristics Design review |  | UM (R&D)
| Deliverable | ü | ü | û | û | APQP Plan | UM APQP Plan | UM (R&D + SQA) + Supplier
CDR | Deliverable | ü | ü | ü | û | Inspection plan & Report for prototype | UM APQP Inspections | UM (SQA)
| Deliverable | ü | ü | û | û | Control plan & inspection methods​ | UM Manufacturing Process Control Plan | UM (SQA) + Supplier
| Homologation of IS |  |  |  |  | Prototype​
| Homologation of IS | ü | ü | û | û | Limitation on lot size based on commodity​ |  | N/A
| Homologation of IS | ü | û | û | û | 100% inspection, double check (*)​ |  | UM (SQA) + Supplier
| Homologation of IS | û | ü | û | û | 100% inspection (*)​ |  | UM (SQA) + Supplier
| Homologation of IS | û | û | ü | û | 100% inspection (*)​ full layout (**) |  | UM (SQA) + Supplier
ISRw | Deliverable | ü | ü | û | û | Supplier manufacturing process flow​ |  | Supplier
| Deliverable | ü | ü | û | û | Control plan & inspection methods​ | UM Manufacturing Process Control Plan | UM (SQA) + Supplier
| Deliverable | ü | û | û | û | Onsite manufacturing audit report​ | UM Supplier Audit Report | UM (SQA)
| Deliverable | ü | ü | ü | ü | Initial Sample file (1) |  | Supplier
| Homologation of IS |  |  |  |  | Initial sample​
| Homologation of IS | ü | ü | ü | ü | Assembly test fit / DVT compliance​ |  | UM (IND)
| Homologation of IS | ü | ü | û | û | Bench test compliance ( if any)​ |  | UM (IND)
| Homologation of IS | ü | ü | û | û | Onsite visit for IS approval​ |  | UM (SQA)
| Homologation of IS | ü | û | û | û | 3 samples inspection / full layout (**)​ |  | Supplier
| Homologation of IS | û | ü | û | û | 1 sample inspection / full layout (**)​ |  | Supplier
| Homologation of IS | û | û | ü | û | 100% Inspection / full layout (**) |  | Supplier
| Homologation of IS | û | û | û | ü | Visual inspection |  | UM (SQA)
| Homologation of IS | ü | ü | û | û | CMM program approval (*)​ |  | UM (SQA) + Supplier
| Homologation of IS |  |  |  |  | Packaging​
| Homologation of IS | ü | ü | û | û | Packaging validated​ |  | UM (CM/APE)
| UM Inspection plans |  |  |  |  | Series​
| UM Inspection plans | ü | ü | û | û | Lot acceptance based on AQL Dynamic rule​ |  | N/A
| UM Inspection plans | ü | û | û | û | Could be limitation on batch size​ |  | N/A
| UM Inspection plans | û | ü | ü | û | No limitation on batch size​ |  | N/A
PRR | Deliverable | ü | û | û | û | Probation period enforced control plan​ | UM Manufacturing Process Control Plan | UM (SQA) + Supplier
| Deliverable | ü | û | û | û | Series inspection report​ | UM APQP Inspections | Supplier
| UM Inspection plans |  |  |  |  | Probation period​
| UM Inspection plans | ü | ü | û | û | Key characteristics capability evidence​ |  | N/A
HR | Deliverable | ü | ü | û | û | IS renewal inspection report definition​ | UM APQP Inspections | UM (SQA)
| 1 Initial Sample file content | ü | ü | ü | ü | Data sheet / Initial sample Inspection report​ | UM APQP Inspections
|  | ü | ü | ü | û | Material / surface treatement certificate​
|  | ü | ü | ü | û | Supplier validation test results​
|  | ü | ü | û | û | Master samples (if any)​
|  | û | û | ü | û | Store samples (if relevant)
|  | ü | ü | ü | ü | REACH/RoHs compliance evidences​
|  | ü | ü | ü | û | Packaging conformity​
(*) Also from Supplier​
(**) 1 to 5 from Supplier according commodity/batch size​